## Risk Register
RISK REGISTER FOR WORK AUTHORITY NUMBER:
Quarrying or Rehabilitation Hazard | Risk No. | Risk Event | Phase |  |  | Sensitive Receptors |  |  |  | Inherent Risk Assessment |  |  | Control Measures | Performance Standards | Residual Risk Assessment |  |  | Monitoring and Ongoing Management |  | Detailed Risk Treatment Plan attached?
[6 empty] | Details of sensitive receptor | Location and proximity to site | How hazard may harm or damage sensitive receptor | Evidence to support assessment | Likelihood | Consequence | Risk Rating |  |  | Likelihood | Consequence | Risk Rating | Aspect to be monitored | Details of monitoring and ongoing management
|  |  | Set up/ Construction | Operations/ Production | Rehabilitation
Accountable Personnel
List Personnel accountable for the implementation, management and review of the Risk Management Plan
Personnel |  |  | Roles and Responsibilities

## Example
RISK REGISTER FOR WORK AUTHORITY NUMBER:
Quarrying or Rehabilitation Hazard | Risk No. | Risk event | Phase |  |  | Sensitive receptors |  |  |  | Inherent Risk Assessment |  |  | Control Measures | Performance Standards | Residual Risk Assessment |  |  | Monitoring and Ongoing Management |  | Detailed Risk Treatment Plan attached?
[6 empty] | Details of sensitive receptor | Location and proximity to site | How hazard may harm or damage sensitive receptor | Evidence to support assessment | Likelihood | Consequence | Risk Rating |  |  | Likelihood | Consequence | Risk Rating | Aspect to be monitored and managed | Details of monitoring and ongoing management
|  |  | Set up/ Construction | Operations/ Production | Rehabilitation
Dust | 1 | Dust landed on house and garden of neighbours - result in inhalation | Yes | Yes | Yes | Neighbouring residences | 400m from site | Health and amenity | Air quality modelling completed by consultant on changes and provided as support. | Possible | Moderate | Medium | ·Train staff on the measures used to reduce dust generation. ·Reduce vehicle speeds to 30km/h maximum. ·During dry consitions, use water tanker on internal roads. · Restrict vehicle movements to watered roads where possible. · Treat exposed stockpiles with dust supressants. · Cease dust producing activities during high winds. · Street sweeping being undertaken on all internal sealed roads | . EPA air quality test (SEPP (AQM)) . Speed limits enforced . All heavy vehicles will use sealed roads . Water spray used as required . Street sweeping to be done weekly | Rare | Minor | Low | Emissions of dust and particles will comply with the EPA limits at the nearest sensitive receptors. | · Three-month dust monitoring program undertaken to determine offsite dust impacts. Six months of moitoring to be undertaken subsequent to approval. · Ongoing dust deposition (nuisance dust) monitoring. | No
Noise | 2 | Excessive noise at any sensitive receptors from processing plant | Yes | Yes | Yes | Neighbouring residences | 400m from site | amenity | Acoustic modelling completed by consultant and provided as support | Likely | Minor | Medium | . Extraction area progresses away from sensitive receptors . Comply with operating hours . When not in use turn off plant, equipment and vehicles . Fit processing plant mufflers and other appropriate noise abatement devices | . EPA SEPP-N1 for noise limits . Only operate during approved hours . Processing plant and equipment is maintained as per manufacture specifications | Unlikely | Minor | Low | Noise at sensitive receptors | . Regular noise compliance monitoring . Document complaints, community engagement activities, and any resulting actions. . Adequacy of control measures will be periodically assessed through routine site inspections and community feedback | No
Execessive ground vibrations and noise caused by blasting | 3 | Impact on amenity and damage to sensitive receptors caused by noise and vibration from blast | Yes | Yes | No | Neighbouring residences | 400m from site | unknown ground conditions | Map and modelling of noise and vibration | Likely | Moderate | High | . Shots designed and documented by a licenced shot firer and reviewed by the quarry manager . Blast hole check and pre-shot inspection . Notify nearby residents of the blast, and its date and time (restricted to between 10am and 4pm weekdays) . Clear blast exclusion zone of all equipment and non-essential personnel . Ensure all equipment and non-essential personnel are in designated safe areas . Ensure that the ground vibration equipment is set up and operational | . Complying to consolidated Work Plan, Blast Management Plan and SOPs . Quarry Manager to contact residents and other affected sensitive receptors | Unlikely | Moderate | Medium | Ground vibration | . First five shots are monitored for ground vibration, then at least one annually . Review blast layout for compliance with the Blast Management Plan (by quarry manager and shot firer) | Yes
Flood | 4 | Flooding or overflow of storm water | Yes | Yes | Yes | Neighbouring residences Vegetation | 250-400m from site | . erosion or sediment . Risk of failure of on-site infrastructure . Turbid water may enter local creek and impact environment | Proximity to site | Unlikely | Major | High | . roads constructed to have diversion drains and culverts to divert clean stormwater away from roads. . Arrange the drainage of roads to be in a vegetated area through erosion protection structures . All surface water collected on site is retained in storage dams to reuse on site, where possible. . Construct, manage and maintain appropriate drainage and holding dam strctures . EPA Discharge Licence for release of water to local creek | . No offsite water release . Maintaining tracks to minimise erosion . Compliance to Workplan and Site Layout Plan | Rare | Moderate | Medium | . Drainage inspection . Inspect effectivness of erosion control structures . EPA Discharge Licence requirements when discharging water | . Inspect and maintain the drain, sediment and erosion control features 6-monthly . Check EPA Discharge Licence conditions | Yes
Accountable Personnel
List Personnel accountable for the implementation, management and review of the Risk Management Plan
Personnel |  |  | Roles and Responsibilities

## Criteria & Matrix
Consequence
Likelihood Ranking | Consequence Ranking |  |  | Insignificant | Minor | Moderate | Major | Critical
Almost Certain | Critical | Likelihood | Almost Certain | Medium | High | Very High | Very High | Very High
Likely | Major |  | Likely | Medium | Medium | High | Very High | Very High
Possible | Moderate |  | Possible | Low | Medium | Medium | High | Very High
Unlikely | Minor |  | Unlikely | Low | Low | Medium | High | High
Rare | Insignificant |  | Rare | Low | Low | Medium | Medium | High
Eliminated |  |  | Eliminated | Eliminated
Phase
Yes
No